## Sheet1
| Day | 2018-03-09 | 2018-03-10 | 2018-03-11 | 2018-03-12 | 2018-03-13 | 2018-03-14 | 2018-03-15 | 2018-03-16 | 2018-03-17 | 2018-03-18 | 2018-03-19 | 2018-03-20 | 2018-03-21 | 2018-03-22 | 2018-03-23 | 2018-03-24 | 2018-03-25 | 2018-03-26 | 2018-03-27 | 2018-03-28 | 2018-03-29 | 2018-03-30 | 2018-03-31 | 2018-04-01 | 2018-04-02 | 2018-04-03 | 2018-04-04 | 2018-04-05 | 2018-04-06 | 2018-04-07 | 2018-04-08 | 2018-04-09 | 2018-04-10 | 2018-04-11 | 2018-04-12 | 2018-04-13 | 2018-04-14 | 2018-04-15 | 2018-04-16 | 2018-04-17 | 2018-04-18 | 2018-04-19 | 2018-04-20 | 2018-04-21 | 2018-04-22 | 2018-04-23 | 2018-04-24 | 2018-04-25 | 2018-04-26 | 2018-04-27 | 2018-04-28 | 2018-04-29 | 2018-04-30 | 2018-05-01 | 2018-05-02 | 2018-05-03 | 2018-05-04 | 2018-05-05 | 2018-05-06 | 2018-05-07 | 2018-05-08 | 2018-05-09 | 2018-05-10 | 2018-05-11 | 2018-05-12 | 2018-05-13 | 2018-05-14 | 2018-05-15 | 2018-05-16 | 2018-05-17 | 2018-05-18
C0 | Project Management | Settling Down
| Selecting Teams | X
| Problem Selection | X
| Creating Gantt Chart |  |  |  | X | X
| Collecting Group Data | X | X | X | X | X
| Present Project Proposal |  |  |  |  | X
| Problem Statement | X | X | X | X | X
C1 | Research |  |  |  | Conducting Research
| Preliminary Research |  |  |  | X | X | X | X | X | X | X | X | X | X
| Justifying Problem |  |  |  | X | X | X | X
| Analyze Prior Solution Attempts | [7 empty] | X | X
| Provide Personal Solution | [9 empty] | X
| Justifying Personal Solution | [10 empty] | X | X
| Preliminary Projects | X
| Topic Background | [7 empty] | X | X | X | X | X | X | X | X | X | X | X
C2 | Design | [18 empty] | Design Process
| STEM Principles and Applications | [18 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
| Concept Drawing of Model | [18 empty] | X | X
| Technical Drawing | [20 empty] | X | X
| Procedure of Design | [22 empty] | X | X | X | X
| Tools and Parts List and Costs | [26 empty] | X | X
| Acquiring Tools and Parts | [28 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
| Reviewing Safety | [26 empty] | X | X
C3 | Prototype and Test | [33 empty] | Prototyping and Testing
| Initial Building of Product | [33 empty] | X | X | X | X | X | X | X | X | X | X | X | X
C4 | Evaluate and Reflect | [57 empty] | Evaluation and Reflection
| External Evaluation | [57 empty] | X | X | X | X | X | X | X
| Designer Reflection | [57 empty] | X | X | X | X
| Designer Recommendations | [61 empty] | X | X | X
C5 | Project Presentation | [62 empty] | Prepare Final Presentations
| Engineering Notebook | [7 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
| Prepare Final Presentation | [62 empty] | X | X | X | X | X | X | X | X | X
| Project Preparation | [68 empty] | X | X | X
| Presentation | [70 empty] | X
| Compiling Portfolio | [62 empty] | X | X | X | X | X | X | X | X | X